## Feature Backlog
Feature ID | Feature Name | Description | Priority | Effort | Impact | RICE Score | Quarter | Status | Owner
F001 | Hybrid LLM Processing | Combine traditional and AI parsing | High | 8 | 9 | 18 | Q1 2024 | In Progress | AI Team
F002 | Real-time Collaboration | Multi-user document editing | Medium | 13 | 7 | 15 | Q2 2024 | Planning | Frontend Team
F003 | Advanced Analytics | Processing metrics dashboard | High | 5 | 8 | 16 | Q1 2024 | Ready | Data Team
F004 | API Rate Limiting | Prevent abuse and ensure stability | Low | 3 | 5 | 8 | Q4 2024 | Backlog | Backend Team
F005 | Multi-format Support | Support for additional file types | Medium | 8 | 6 | 12 | Q3 2024 | Research | AI Team
F006 | User Authentication | OAuth and SSO integration | High | 5 | 9 | 18 | Q1 2024 | Complete | Security Team
F007 | Mobile App | iOS and Android applications | Low | 21 | 4 | 6 | Q1 2025 | Idea | Mobile Team
F008 | Batch Processing | Handle large document sets | Medium | 8 | 7 | 14 | Q2 2024 | Planning | Backend Team

## Technical Debt
Debt ID | Component | Issue | Severity | Effort | Impact on Performance
TD001 | Document Parser | Legacy PDF parsing library | Medium | 5 | 20% slower processing
TD002 | Database | Missing indexes on queries | High | 2 | 3x slower API responses
TD003 | API | No request validation | High | 3 | Security vulnerability
TD004 | Frontend | Outdated React version | Low | 8 | Maintenance burden
TD005 | Monitoring | No application metrics | Medium | 4 | No visibility into issues

## Success Metrics
Metric | Current Value | Target Value | Timeline | Measurement Method
Processing Accuracy | 75% | 95% | Q2 2024 | Manual validation of 100 random documents
Processing Speed | 30 sec/doc | 5 sec/doc | Q1 2024 | Average processing time measurement
User Satisfaction | 3.2/5 | 4.5/5 | Q3 2024 | Quarterly user survey
System Uptime | 95% | 99.9% | Q2 2024 | Automated monitoring alerts
API Response Time | 500ms | 100ms | Q1 2024 | Performance monitoring tools